## Defect_Register
Defect ID | Title | Severity | Confidence | Affected Module | Location | Reproduction Steps | Expected Result | Actual Result | Evidence Reference | Impact | Exception Implications | Remediation / Recommendation | Regression Requirements | Status
DEF-001 | Cleartext Supabase Pooler Credentials in application-supabase.yml | P0 Critical | Confirmed | Security & Infrastructure | backend/src/main/resources/application-supabase.yml:lines 3-6 | 1. Open application-supabase.yml. 2. Observe datasource URL, username (postgres.irwiiyowpppdynbmwwuz), and password (MyDbSporekart@123#) committed in source. | Database credentials must be supplied via environment variables (e.g. ${SUPABASE_DB_PASSWORD}) or cloud secrets manager. | Direct production database connection strings and plain passwords are committed to the code repository. | application-supabase.yml lines 3-6: url: jdbc:postgresql://aws-0-ap-northeast-1.pooler.supabase.com:6543/postgres?prepareThreshold=0 | Full database compromise, catastrophic data exfiltration, unauthorized modification, or complete database wiping. | Authentication failures on rotation will trigger unhandled HikariPool connection exceptions and application startup crash. | Immediately rotate the Supabase database password in the Supabase console, purge git history via git filter-repo, and bind Spring datasource properties to environment variables. | Pre-commit git secret detection hook (e.g. gitleaks / git-secrets) scanning all yml/properties files. | Residual Operational Risk (Requires Secret Rotation in Cloud Console)
DEF-002 | High and Critical Severity Vulnerabilities in Frontend Dependencies | P0 Critical | Confirmed | Frontend Architecture & Dependencies | frontend/package.json & frontend/package-lock.json | 1. Navigate to frontend/ directory. 2. Execute 'npm audit --audit-level=high'. 3. Review reported advisories. | Zero High or Critical vulnerabilities in dependency tree. | 15 vulnerabilities detected, including Critical RCE in tinypool <= 2.1.1 and High DoS in source-map-js. | npm audit report output: 15 vulnerabilities (4 moderate, 9 high, 2 critical). Tinypool CVE-2024-xxxx, source-map-js advisory. | Remote code execution during developer build or Vitest worker threads; denial of service in bundle processing. | Worker thread execution crashes with uncaught unhandled exceptions during build / CI runs. | Execute 'npm update' or pin patched subdependencies in overrides block of package.json. Upgrade tinypool to >= 2.1.2. | Automated Dependabot / Renovate scanning with CI gate blocking merges on High/Critical vulnerabilities. | Residual Staging Constraint (Upgradable via package.json overrides)
DEF-003 | Static Hardcoded Fallback JWT Secret in Dev and Test Profiles | P1 High | Confirmed | Identity & Authentication | backend/src/main/resources/application-dev.yml:line 32 & application-test.yml:line 19 | 1. Launch backend without setting JWT_SECRET environment variable. 2. Application bootstraps using static fallback string 'SporekartSecureJwtSecretKeyMustBeLongEnoughForHS256Algorithm2026'. 3. Forge JWT token signed with this secret string. 4. Call protected endpoint /api/v1/customer/profile with forged token. | Application must fail to start in non-test profiles if JWT_SECRET is missing, or generate an ephemeral random startup secret. | Application silently uses known public fallback key; attackers knowing the secret can forge valid admin tokens. | application-dev.yml: secret: ${JWT_SECRET:SporekartSecureJwtSecretKeyMustBeLongEnoughForHS256Algorithm2026} | Complete authentication bypass and administrative privilege escalation if dev/test profile settings leak to staging/prod. | Signature validation succeeds for forged tokens, allowing malicious requests to bypass security filter chain. | Remove static fallback from application-dev.yml. Fail application bootstrap with ApplicationContextException if JWT_SECRET is unset. | Automated security test verifying application context failure when JWT_SECRET is empty in staging/production mode. | Open / Backlog
DEF-004 | Partial Failure & Financial Drift in Order Cancellation Wallet Refund | P1 High | Confirmed | Orders & Wallet Integration | backend/src/main/java/com/sporekart/order/application/OrderService.java:lines 440-456, 458-470 | 1. Create and pay for an order worth INR 3,500. 2. Simulate transient failure in walletService.processRefundToWallet() (e.g. wallet lock timeout). 3. Trigger POST /api/v1/orders/{id}/cancel. 4. Observe OrderService catches and logs exception but continues execution, marking order CANCELLED. | If wallet refund credit fails, the cancellation transaction must roll back or queue a resilient retry outbox event. | Order is marked CANCELLED in database, but customer wallet is credited INR 0, stranding customer funds in limbo. | OrderService.java line 520: } catch (Exception e) { log.error("Error crediting wallet...", e); } order.setStatus(newStatus); orderRepository.save(order); | Customer financial loss, unrecorded liability in ledger, reconciliation breakdown, customer support escalation. | Swallowing Exception prevents Spring transaction rollback, committing partial mutation to PostgreSQL. | Rethrow custom OrderCancellationRefundException to force transaction rollback, or implement a transactional outbox pattern for refunds. | Unit test verifying rollback when processRefundToWallet throws runtime exception during cancellation. | Resolved / Hardened in Phase 8
DEF-005 | JPA @Transactional Silent Rollback Violation in Webhook Handling | P1 High | Confirmed | Payments & Webhooks | backend/src/main/java/com/sporekart/payment/application/PaymentService.java:lines 225, 236-240 | 1. Send duplicate Razorpay payment.captured webhook with same event_id concurrently. 2. Both threads enter @Transactional processWebhook. 3. Second thread hits DataIntegrityViolationException on paymentEventRepository.save(event). 4. Catch block catches exception and returns 200 message string. 5. Transaction commit fails with UnexpectedRollbackException, returning HTTP 500 to Razorpay. | Duplicate webhook events must be ignored idempotently and return HTTP 200 OK without triggering transaction rollback. | Hibernate marks session rollback-only upon constraint violation; commit triggers UnexpectedRollbackException, causing HTTP 500 and gateway retry storm. | PaymentService.java lines 236-239: catch (DataIntegrityViolationException dive) { log.warn(...); return "Webhook event already processed"; } | Razorpay enters exponential retry backoff storm, overwhelming server with redundant webhook requests for 24 hours. | UnexpectedRollbackException bubbles to GlobalExceptionHandler, which returns generic HTTP 500 error envelope. | Extract idempotency verification and event recording into separate service with @Transactional(propagation = Propagation.REQUIRES_NEW). | Integration test sending identical concurrent webhook payloads and asserting HTTP 200 OK without rollback exceptions. | Resolved / Hardened in Phase 9
DEF-006 | Concurrency Race Condition on Masterclass Batch Capacity Reservation | P1 High | Confirmed | Training & Enrollment | backend/src/main/java/com/sporekart/training/application/TrainingService.java:lines 175-195 | 1. Seed a batch with capacity = 10, enrolled_count = 9 (1 seat left). 2. Send 5 simultaneous POST /api/v1/training/enrollments requests from different users. 3. Observe enrolled_count increments beyond capacity to 14 without database lock rejection. | Database must reject requests exceeding capacity using pessimistic locking or conditional UPDATE (WHERE enrolled_count < capacity). | Enrolled count exceeds capacity, allowing oversubscription of physical workshop seats. | 12 training batches in staging database exhibited enrolled_count > capacity following synthetic concurrency tests (audit_output/check_catalog_and_batches.py). | Physical workshop classroom overcrowding, logistical breakdown, refund liabilities, breach of customer trust. | BatchCapacityExceededException is only checked in memory before concurrent updates bypass the check. | Use SELECT FOR UPDATE (PESSIMISTIC_WRITE) on Batch entity or execute atomic UPDATE batches SET enrolled_count = enrolled_count + 1 WHERE id = :id AND enrolled_count < capacity. | Concurrent thread test booking last available seat across 20 threads, asserting exactly 1 success and 19 rejections. | Resolved / Hardened in Phase 11
DEF-007 | Inventory Stock Reservation Race Condition Under Concurrent Checkouts | P1 High | Confirmed | Catalog & Inventory | backend/src/main/java/com/sporekart/order/application/OrderService.java & InventoryRepository.java | 1. Set product variant stock to 1. 2. Trigger 10 concurrent checkout requests for that product variant. 3. Multiple checkouts pass available_quantity check before stock is decremented. | Exactly 1 order placed; other 9 rejected with HTTP 409 Insufficient Stock. | Race condition permits 2 or more orders to be placed against single stock unit prior to decrement. | Performance concurrency benchmark test results: 226 collision errors under concurrent thread bursts. | Overselling physical stock, order fulfillment delays, negative customer reviews, cancellation costs. | OptimisticLockException or late stock validation throws after order is created, requiring manual cancellation. | Use pessimistic locking on inventory rows during checkout stock reservation, or atomic database decrement queries. | Concurrent stress test purchasing stock unit = 1 with 20 parallel threads. | Resolved / Hardened in Phase 8
DEF-008 | Database Schema Drift: V37 Flyway Migration Missing from Supabase Directory | P1 High | Confirmed | Database & Migrations | backend/supabase/migrations/ vs backend/src/main/resources/db/migration/ | 1. Compare directory contents between db/migration/ and supabase/migrations/. 2. Observe V37__deduplicate_and_unique_active_user_cart.sql existed in Spring Flyway directory but was absent in Supabase directory. | All database migrations must be mirrored identically across Spring Boot Flyway and Supabase CLI directories. | Direct Supabase CLI deployments (supabase db push) did not apply V37 partial unique index on active carts. | Diff between backend/src/main/resources/db/migration and backend/supabase/migrations revealed missing V37 and unapplied V39. | Schema divergence between local development, Supabase staging, and production environments; duplicate active carts. | Missing database constraints allow duplicate cart insertion, corrupting user checkout sessions. | Created 20261017000039_v39__reconcile_and_add_foreign_key_indexes.sql and mirrored V37 into supabase/migrations. | CI pipeline check comparing file hashes between db/migration/ and supabase/migrations/. | Resolved / Reconciled in Phase 5
DEF-009 | Missing Foreign Key Indexes on 9 High-Traffic Relational Tables | P1 High | Confirmed | Database Performance | backend/src/main/resources/db/migration/V39__reconcile_and_add_foreign_key_indexes.sql | 1. Run PostgreSQL query inspecting pg_stat_user_tables and pg_indexes for foreign key columns. 2. Note unindexed foreign keys on cart_items.cart_id, order_items.order_id, wallet_transactions.wallet_id, etc. | All foreign key columns must possess B-tree indexes to support fast joins and prevent full table locks on parent table deletes. | PostgreSQL performed sequential table scans for foreign key constraint checks and relational joins. | Database integrity scan identified 9 unindexed foreign key relationships in public schema. | Query latency degradation, CPU spikes, table locks during order/cart item deletions as dataset grows. | Query timeout exceptions (QueryTimeoutException / 504 Gateway Timeout) under high transaction volumes. | Deployed Flyway migration V39 adding 14 targeted indexes covering all relational joins and filter paths. | Automated SQL schema test verifying that 100% of foreign key constraints have matching indexes. | Resolved / Reconciled in Phase 5
DEF-010 | Unbounded Heap Memory Consumption in AbandonedCartScheduler | P2 Medium | Confirmed | Notifications & Schedulers | backend/src/main/java/com/sporekart/notification/application/AbandonedCartScheduler.java:lines 47-50 | 1. Inspect AbandonedCartScheduler.scanAbandonedCarts() source code. 2. Note cartRepository.findAll() loads every cart in the database into JVM memory. 3. Carts are filtered in memory via stream().filter(c -> c.getStatus() == CartStatus.ACTIVE). | Scheduler should query only abandoned carts via indexed SQL query (e.g. findByStatusAndUpdatedAtBefore(ACTIVE, cutoff, Pageable)). | Entire carts table is loaded into memory every 15 minutes, consuming O(N) memory and holding JDBC connection open. | AbandonedCartScheduler.java: List<Cart> activeCarts = cartRepository.findAll().stream().filter(...).collect(Collectors.toList()); | JVM OutOfMemoryError (OOM) and GC pause spikes as total historical carts exceed tens of thousands. | OOM in scheduler thread crashes background execution and degrades entire Spring Boot application responsiveness. | Replace findAll().stream() with parameterized repository query using pagination: findAbandonedActiveCarts(cutoffTime, PageRequest.of(0, 50)). | Static code analysis rule forbidding findAll() calls in scheduled service methods. | Open / Technical Debt
DEF-011 | Scheduled Daemons Lack Per-Item Exception Boundaries (Batch Failure Cascade) | P2 Medium | Confirmed | Background Workers & Schedulers | backend/src/main/java/com/sporekart/notification/application/AbandonedCartScheduler.java & BlogContentService.java | 1. Schedule 5 blog posts due for publishing. 2. Invalidate slug or title on post #2 to trigger validation failure on save. 3. Execute BlogContentService.processScheduledPosts(). 4. Observe uncaught exception on post #2 rolls back entire transaction; posts 1, 3, 4, 5 are never published. | Each scheduled item should be processed in its own try/catch block so a single bad record does not block remaining items. | A single corrupt record aborts the loop, rolls back the transaction, and repeats the crash every minute. | BlogContentService.java: @Scheduled @Transactional public void processScheduledPosts() { for (BlogPost post : duePosts) { post.publish(); postRepository.save(post); } } | Platform-wide publishing paralysis; automated cart abandonment emails completely halted. | Transactional rollback-only causes scheduled worker starvation. | Wrap per-item logic in try/catch, log failures individually, and record item-level error status without aborting batch. | Unit test simulating single-item failure in batch and asserting remaining items process successfully. | Open / Technical Debt
DEF-012 | Uncaught Asynchronous Exception Drop & Missing AsyncUncaughtExceptionHandler | P2 Medium | Confirmed | Analytics & Event Bus | backend/src/main/java/com/sporekart/analytics/application/AnalyticsEventListener.java:lines 22-120 | 1. Trigger ProductViewed event with product title containing unescaped double quotes (e.g. 2.5" Mushroom Bag). 2. String.format creates invalid JSON in eventDataJson. 3. analyticsEventRepository.save(entity) throws database or JSON parsing exception in worker thread. | Async exceptions should be captured by custom AsyncUncaughtExceptionHandler, logged with structured MDC, and routed to DLQ. | Spring defaults to SimpleAsyncUncaughtExceptionHandler, printing a single unmonitored log line; event is silently dropped. | AnalyticsEventListener.java: All 8 listener methods are @Async public void without try/catch or custom exception handler. | Silent loss of business analytics events, distorted conversion funnel metrics, untracked user behavior. | Calling thread is unaware of failure because void @Async methods return immediately without awaiting result. | Implement AsyncConfigurer with custom AsyncUncaughtExceptionHandler and serialize JSON using Jackson ObjectMapper instead of String.format. | Test publishing malformed event payload and asserting dead-letter queue or error metric increment. | Resolved / Hardened in Phase 12
DEF-013 | Systemic HTTP Status Mapping Inconsistency (404 Converted to 400 Bad Request) | P2 Medium | Confirmed | API & Exception Handling | backend/src/main/java/com/sporekart/shared/application/GlobalExceptionHandler.java & 8 Domain Services | 1. Send GET /api/v1/content/posts/non-existent-slug. 2. Observe service throws IllegalArgumentException("Blog post not found..."). 3. GlobalExceptionHandler maps IllegalArgumentException to HTTP 400 BAD REQUEST. | Missing resources should return HTTP 404 NOT FOUND with ResourceNotFoundException. | HTTP 400 BAD REQUEST returned instead of 404 NOT FOUND. | audit_output/06_BACKEND_EXCEPTION_HANDLING_AUDIT.md: 28 occurrences across TrainingService, SupportApplicationService, ShippingService, etc. | Frontend error handlers cannot distinguish client payload syntax errors from missing resources; SEO crawlers misindex dead links as client bugs. | API contract violation against REST standards (RFC 9110). | Replace IllegalArgumentException with ResourceNotFoundException across entity lookup .orElseThrow() invocations. | Automated API contract test asserting HTTP 404 for all non-existent entity IDs across all public and protected routes. | Resolved / Hardened in Phase 3
DEF-014 | Missing Framework Exception Handlers in GlobalExceptionHandler | P2 Medium | Confirmed | API & Error Handling | backend/src/main/java/com/sporekart/shared/application/GlobalExceptionHandler.java:lines 18-106 | 1. Send POST /api/v1/cart/items with malformed JSON body: {"productId": "abc",}. 2. Spring throws HttpMessageNotReadableException. 3. Because handler is missing, exception falls through to @ExceptionHandler(Exception.class), returning HTTP 500. | Malformed JSON syntax should return HTTP 400 Bad Request with code MALFORMED_JSON_REQUEST. | HTTP 500 INTERNAL_SERVER_ERROR returned with generic server failure message. | GlobalExceptionHandler.java lacked explicit handlers for HttpMessageNotReadableException, MethodArgumentTypeMismatchException, etc. | False-positive 500 alerts in production APM monitoring; poor developer/client integration experience. | Normal client-side input errors trigger high-severity server incident alerts. | Add explicit handlers for HttpMessageNotReadableException, MethodArgumentTypeMismatchException, HttpRequestMethodNotSupportedException. | Contract test verifying HTTP 400 on malformed JSON and HTTP 405 on unsupported HTTP methods. | Resolved / Hardened in Phase 3
DEF-015 | Code Clones & Duplication Between Checkout and Trainee Profile Forms | P2 Medium | Confirmed | Frontend Architecture | frontend/src/pages/CheckoutPage.jsx & frontend/src/components/TraineeProfileEnrollmentModal.jsx | 1. Run jscpd linter on frontend/src. 2. Observe 99 code clones with 1,592 duplicated lines identified between CheckoutPage and TraineeProfileEnrollmentModal. | Shared address form fields, state/city dropdowns, and PIN lookup logic should be abstracted into a single reusable component. | Duplicated JSX form markup and validation logic led to inconsistent bug fixes across checkout and training enrollment. | jscpd-report/jscpd-report.json: 99 clones, 1,592 duplicate lines. | High maintenance overhead; bug fixes applied to checkout address logic did not automatically propagate to training enrollment modal. | Form validation errors handled differently between checkout and training pages. | Extracted shared IndianAddressForm component used uniformly across CheckoutPage, DashboardPage, and TraineeProfileEnrollmentModal. | jscpd quality gate in package.json asserting clone percentage < 5%. | Resolved in Phase 16
DEF-016 | Admin Order and Invoice Retrieval IDOR Restriction | P2 Medium | Confirmed | Orders & Support | backend/src/main/java/com/sporekart/order/application/OrderService.java:lines 268-278 | 1. Authenticate as admin user (ROLE_ADMIN). 2. Request customer order details via GET /api/v1/orders/{orderId} or invoice via /orders/{orderId}/invoice. 3. OrderService checks order.getUserId().equals(currentUserId), rejecting admin with HTTP 403 Forbidden. | Admin operators with ROLE_ADMIN should be authorized to inspect customer orders and generate invoices. | Admins could only access orders via dedicated admin endpoint, breaking support deep-links and shared invoice links. | OrderService.java: if (!order.getUserId().equals(userId)) { throw new ForbiddenOperationException(...); } without checking role. | Operational impediment for customer support agents trying to view invoices from support tickets. | ForbiddenOperationException thrown instead of allowing administrative privilege delegation. | Update validateOrderAccess to permit access if order.getUserId().equals(userId) OR currentUser.hasRole('ROLE_ADMIN'). | Test asserting admin can view customer order invoice while customer cannot view other customers' orders. | Resolved / Hardened in Phase 8
DEF-017 | Phone Number Country Code Regex Collision in validateIndianPhone | P3 Low | Confirmed | Frontend Validation | frontend/src/utils/validation.js:validateIndianPhone | 1. Enter valid 10-digit Indian phone number starting with '91' (e.g. 9111320655). 2. Regex cleaned.replace(/^(?:\+91¦91¦0)/, '') stripped leading '91', leaving 8 digits (11320655). 3. Validation returned 'Valid 10-digit Indian mobile number is required'. | 10-digit numbers starting with 91 must not have 91 stripped; only 12-digit numbers starting with 91 should strip prefix. | Legitimate phone numbers starting with 91 were rejected as invalid. | Playwright E2E checkout test failed when test phone number was 9111320655. | Valid customers with phone numbers beginning with 91 were blocked from completing checkout and training enrollment. | Client-side form validation blocked submission before API call was made. | Fixed regex in validation.js to check string length before stripping country code: if (cleaned.length === 12 && cleaned.startsWith('91')) cleaned = cleaned.slice(2). | Unit test asserting validateIndianPhone('9111320655') returns null error. | Resolved & Verified in Phase 16
DEF-018 | Jackson Boolean Property Getter Serialization Discrepancy | P3 Low | Confirmed | Training API & DTOs | backend/src/main/java/com/sporekart/training/api/TrainingDtos.java:BatchSlotResponse | 1. Inspect serialized JSON response from GET /api/v1/training/courses. 2. Java boolean field isAvailable with getter isAvailable() serialized as JSON key 'available' by Jackson. 3. Frontend template checked slot.isAvailable, which evaluated to undefined. | JSON key should match frontend expectations (isAvailable) or frontend should check both available and isAvailable. | Available batch slots rendered as disabled/full in frontend masterclass catalog. | Playwright test 09_training_enrollment.spec.js timed out waiting for active batch slot buttons. | Prospective trainees could not click 'Select Slot' on open courses with seats available. | No backend exception; purely silent API serialization contract mismatch. | Annotated BatchSlotResponse.isAvailable with @JsonProperty("isAvailable") and added defensive frontend check (slot.isAvailable ¦¦ slot.available). | Integration test validating JSON key 'isAvailable' is present in BatchSlotResponse payload. | Resolved & Verified in Phase 16
DEF-019 | Address Form State Synchronization Race Condition with Async PIN Code Lookup | P3 Low | Confirmed | Frontend Components | frontend/src/components/IndianAddressForm.jsx | 1. Type PIN code 560001 (triggers async postal lookup). 2. Immediately begin typing phone number before lookup resolves. 3. When lookup resolves, updateForm({ state, city }) called with stale formData closure, wiping the phone number input. | Asynchronous PIN lookup should merge into latest form state without overwriting concurrent inputs. | Phone number field was wiped blank upon PIN lookup completion, causing form validation failure on submit. | Playwright test 09_training_enrollment snapshot showed focused, empty Primary Phone input despite fill action. | Users had their phone numbers cleared unexpectedly when entering address details rapidly. | Form validation failed on client submit, preventing navigation to payment gateway. | Updated IndianAddressForm to synchronously update formDataRef.current and dispatch functional state updates (onChange(prev => ({ ...prev, ...patch }))). | E2E test rapidly typing PIN code and phone number, verifying both values are retained. | Resolved & Verified in Phase 16
DEF-020 | SEO Meta Description Length Underflow on About and Contact Pages | P3 Low | Confirmed | SEO & Metadata | frontend/src/pages/AboutPage.jsx & frontend/src/pages/ContactPage.jsx | 1. Run 'npm run seo:gate'. 2. Note description lengths for /about (61 chars) and /contact (58 chars) fell below the 70-character threshold. | Meta descriptions must be between 70 and 160 characters for optimal search snippet display. | SEO quality gate flagged warnings on meta description length underflow. | scripts/seo-quality-gate.js execution logs: /about meta description length 61 < 70. | Search engine snippet truncation, reduced search engine click-through rates (CTR). | Build gate warning in CI. | Expanded meta descriptions to comprehensive, keyword-rich summaries (> 120 characters). | Automated SEO gate asserting 100% of routes meet 70-160 character description constraints. | Resolved & Verified in Phase 16
DEF-021 | 306 Non-Fatal ESLint Warnings Across Frontend Modules | P4 Informational | Confirmed | Frontend Code Quality | frontend/src/ (multiple files) | 1. Run 'npm run lint'. 2. Observe 306 warnings for unused React imports and unused Lucide icon imports. | Clean linter output with zero warnings and zero errors. | 306 warnings reported; if --max-warnings 0 is enforced in package.json, CI build fails. | npm run lint output: 0 errors, 306 warnings. | Code clutter, minor bundle bloat from unused imports (partially mitigated by Vite tree-shaking). | No runtime implications. | Remove unused 'import React' declarations across JSX files and prune unused Lucide icon imports. | Configure ESLint --max-warnings threshold to ratcheted target during refactoring sprints. | Open / Technical Debt
DEF-022 | Staging Fallbacks for Real External Delivery Channels (SMS & SMTP) | P4 Informational | Confirmed | External Integrations | backend/src/main/resources/application.yml & application-dev.yml | 1. Inspect TwilioSmsService.java and NotificationWorker.java. 2. Note USE_REAL_TWILIO_SMS=false and SMTP fallback to application log sink in local staging. | Production environment must connect to live authenticated Twilio and JavaMailSender SMTP gateways. | Staging operates safely in mock/log mode to prevent accidental SMS billing or test email delivery to real recipients. | NotificationWorker log output: [NOTIFICATION DISPATCHED - LOG MODE] Event ID: ... | Live external carrier deliverability (DLR receipt, spam score, inbox placement) cannot be verified in staging without real credentials. | Third-party network timeouts and carrier rate limits are bypassed in mock mode. | Maintain mock mode for CI/staging. Require live credentials verification during production deployment sign-off. | Dedicated smoke test in pre-production verifying live SMS dispatch to verified operator phone number. | Residual Staging Constraint