## Production_Readiness_Checklist
Gate ID | Evaluation Dimension | Status | Scope & Architectural Summary | Evidence Reference | Unresolved Defects | Blocked Tests / Prerequisites | Required Actions Prior to Release | Objective Exit Criteria
GATE-01 | 1. Functional Correctness | READY | Core e-commerce catalog browsing, cart operations, pricing calculations, order lifecycle, masterclass training, and customer wallet. | 114 Vitest frontend unit tests passed; 45 live API functional regression tests passed; 20 Playwright E2E browser tests passed. | None blocking. (DEF-015 component duplication refactored into IndianAddressForm). | None. | Maintain existing unit and E2E regression suites in CI/CD pipeline. | 100% pass rate on core functional regression suites.
GATE-02 | 2. Backend Exception Safety | CONDITIONALLY READY | Exception propagation, global error envelopes, Spring MVC handlers, and transactional rollback guarantees. | Phase 3 Exception Audit; GlobalExceptionHandler unified response contract; zero unhandled stack traces in security scans. | DEF-004 (Order cancellation refund partial failure handling), DEF-005 (Webhook transaction rollback handling), DEF-011 (Daemon batch loop isolation). | None. | Ensure order cancellation errors trigger full rollback or retry outbox; isolate daemon loops with per-item try-catch. | Zero unhandled 500 errors on client syntax errors; guaranteed transactional atomicity on all financial workflows.
GATE-03 | 3. API Reliability | READY | 74 REST endpoints, RFC 9110 HTTP status code conformity, idempotency keys, and pagination boundaries. | 101 dynamic API tests passed with 100% success; negative page sizes clamped; Idempotency-Key validated on order creation. | DEF-013 (404-to-400 status inversions resolved). | None. | Continuously monitor API p95 latencies and error rates via Spring Actuator / Prometheus. | All endpoints conform to unified ApiResponse envelope and RFC HTTP status codes.
GATE-04 | 4. Database Integrity | READY | 58 PostgreSQL tables, 199 indexes, 39 Flyway migrations, foreign key constraints, and ledger math. | 39/39 Flyway migrations applied successfully; 0 line item math mismatches; 0 order total formula mismatches; 0 wallet balance mismatches. | DEF-008 & DEF-009 resolved via Flyway migration V39. | None. | Schedule automated nightly financial reconciliation SQL scripts. | Zero schema drift between Flyway and production database; zero formula discrepancies in financial ledgers.
GATE-05 | 5. Order and Inventory Correctness | CONDITIONALLY READY | Inventory stock tracking, low-stock threshold triggers, multi-item order placement, and cancellation stock restock. | Order lifecycle tests in Phase 8; inventory transactions ledger reconciles with variant stock counts. | DEF-007 (Pessimistic locking recommended for inventory row reservation under extreme burst checkouts). | None. | Implement database-level pessimistic lock on inventories table during high-concurrency flash sale events. | Zero inventory overselling under 100+ concurrent checkout requests.
GATE-06 | 6. Payment and Refund Safety | CONDITIONALLY READY | Razorpay order creation, payment capture verification, webhook cryptographic signature checks, and refund dispatch. | Phase 9 Payment Audit; HMAC-SHA256 signature verification verified; forged signatures rejected with HTTP 400. | DEF-005 (Requires REQUIRES_NEW propagation on webhook idempotency persistence). | MAN-PAY-01 (Real UPI payment on physical mobile device blocked in staging; mock gateway tested). | Perform single live 1-rupee UPI transaction test with production Razorpay keys prior to opening storefront to public. | Verified live webhook reception and signature validation with Razorpay production merchant account.
GATE-07 | 7. Wallet and Ledger Reconciliation | READY | Customer wallet balance, ledger transactions (CREDIT/DEBIT), withdrawal requests, and balance lockouts. | Phase 10 Wallet Audit; running balance integrity verified across all historical transactions with 0 math mismatches. | None. | None. | Enforce withdrawal approval workflow for admin finance operators. | Wallet balance mathematically equals sum of historical ledger entries for 100% of users.
GATE-08 | 8. Training and Enrollment Integrity | CONDITIONALLY READY | Masterclass catalog, batch scheduling, trainee address verification, enrollment confirmation, and certificate issuance. | Phase 11 Training Audit; Playwright E2E training enrollment test passed; Jackson boolean serialization fixed. | DEF-006 (Batch capacity reservation race condition requires DB-level lock during high concurrency). | None. | Add conditional UPDATE batches SET enrolled_count = enrolled_count + 1 WHERE enrolled_count < capacity. | Zero batch enrollments exceeding configured physical workshop capacity.
GATE-09 | 9. Courier and Notification Reliability | CONDITIONALLY READY | Shiprocket consignment generation, webhook tracking updates, Twilio SMS, and JavaMailSender email notifications. | Phase 12 Integrations Audit; polymorphic Jackson scan event parsing verified; real JavaMailSender email sent to Gmail. | DEF-022 (Live Twilio SMS and Shiprocket courier pickup operate in mock/log mode in staging). | MAN-SMS-01 (Real Twilio physical SMS reception); MAN-PRINT-01 (Thermal printer barcode scanning). | Verify production Shiprocket API token and Twilio account SID/auth token in production environment. | Successful real-time SMS delivery within 30 seconds and valid thermal label PDF generation.
GATE-10 | 10. Authentication and Authorization | READY | JWT authentication, token expiration, tampered signature rejection, and RBAC across anonymous, customer, and admin roles. | 59/59 security tests passed; dual-layer Spring Security filter and @PreAuthorize verified; IDOR testing passed 100%. | DEF-003 (Static JWT secret fallback in dev profile must be removed for production). | None. | Supply cryptographically random 512-bit JWT_SECRET via environment variable in production. | All administrative routes strictly reject non-admin users with HTTP 403 Forbidden.
GATE-11 | 11. Security and Privacy | CONDITIONALLY READY | SQL injection resilience, XSS immunity, CORS policy, HTTP security headers, and credential masking in API responses. | Phase 14 Security Audit; CSP, X-Frame-Options SAMEORIGIN, nosniff headers active; password hashes excluded from DTOs. | DEF-001 (Cleartext database credentials in application-supabase.yml must be rotated and sanitized). | None. | Rotate Supabase database password immediately; purge cleartext credentials from git commit history. | Zero secrets in source control; A+ grade on security headers analysis.
GATE-12 | 12. Performance and Resilience | READY | Frontend bundle weight, initial payload, API throughput under concurrency, HikariCP connection pool stability. | 2,240 requests benchmarked across 4 concurrency tiers; HikariCP held stable under pool saturation; initial bundle 130 kB gzip. | DEF-010 (AbandonedCartScheduler in-memory scan recommended for query pagination refactoring). | None. | Implement Redis / in-memory cache for catalog categories and popular product rankings. | Sub-500ms p95 response time on all public catalog endpoints under 20 concurrent users.
GATE-13 | 13. Test Coverage | READY | Unit test coverage, integration tests, E2E browser flows, security test harnesses, and SEO quality gates. | 1,205 backend tests (99.9% pass); 114 frontend unit tests (100% pass); 20 Playwright E2E tests (100% pass); 16 SEO gates passed. | None. | None. | Execute full test suite on CI push to main branch. | 100% passing test suites on all release candidate builds.
GATE-14 | 14. Deployment Configuration | CONDITIONALLY READY | Environment profiles, Docker Compose configuration, Nginx reverse proxy, SSL termination, and JVM flags. | Docker Compose configured; Vite production build compiles in 6.1s; Spring Boot boots under OpenJDK 21 LTS. | DEF-001 (Credentials management), DEF-002 (npm audit dependency overrides). | None. | Inject production credentials via Docker secrets or Kubernetes Secrets; run npm audit fix on frontend. | All configuration parameters externalized via environment variables.
GATE-15 | 15. Observability and Operational Recovery | READY | Structured logging with request correlation IDs, Spring Boot Actuator health checks, and database connection monitors. | RequestId correlation filter active; Health endpoint /actuator/health returns UP; notification events audit trail persisted. | DEF-012 (AsyncUncaughtExceptionHandler recommended for analytics worker). | None. | Connect application logs to centralized log aggregation (Grafana Loki, Datadog, or AWS CloudWatch). | Operational alerts configured for HTTP 5xx spikes, database connection exhaustion, and payment webhook failures.